## Local Agency
Status of Active or Programmed FHWA-Funded Transportation Projects
Enter Local Agency Name Here
Enter Date Here
Sponsor Single Point of Contact (Name):
Sponsor Single Point of Contact (Phone #):
Sponsor Single Point of Contact (E-Mail):
# | County | Sponsor | Project Title | Project Location and Description (brief) | Local Agency Project Number | Unique Identifier | TIP ID | Federal Project Number |  | Total Federal $ Amount Programmed to project | Total Federal $ Amount Authorized in E-76 (To-Date) | Total Federal $ Amount Expended (To-Date) | Federal Fund Program(s) | Federal Project Status (Active or Programmed) | Project Delivery Milestones Estimated (E) or Actual (A) Dates | [32 empty] | Project Manager
[9 empty] | Federally Funded Phase(s) | [5 empty] | TIP Approval (Actual Date Only) |  | CT Field Review (if Applicable) | CTC Allocation (if Applicable) | PE E-76 RFA Submitted (Actual Date Only) (if applicable) |  | PE Auth Deadline (if applicable) | PE Auth (E-76) Approval (if applicable) | NEPA Env Doc Approval (required) |  | ROW E-76 RFA Submitted (Actual Date Only) (if applicable) |  | ROW Auth Deadline (if applicable) | ROW Auth (E-76) Approval (if applicable) | ROW Certification (Required) |  | CON E-76 RFA Submitted (Actual Date Only) |  | CON Auth Deadline | CON Auth (E-76) Approval |  | Advertise |  | Award |  | Begin Construction |  | Project Open to Public |  | Most Recent Invoice Paid by Caltrans |  | Federal Project Close Out |  | (Name Phone # Email) | Comments
Enter Local Agency Name Here
1 | SAMPLE | SAMPLE | SAMPLE | SAMPLE | 13-003 | HSIP3-04-57 | REG-130001 | CML-1234(012) | PE/CON | 2306000 | 2306000 | 1871893 | CMAQ | Active | 2007-01-26 | (A) | 2007-03-25 | N/A | N/A | (A) | N/A | N/A | 2008-05-30 | (A) | N/A | (A) | N/A | N/A | 2008-11-01 | (A) | 2008-11-15 | (A) | 2009-04-30 | 2009-01-29 | (A) | 2009-04-10 | (A) | 2009-05-18 | (A) | 2009-11-02 | (A) | 2011-10-19 | (A) | 2011-01-23 | (A) | 2011-04-12 | (E)
2 |  |  | NOTE: Rename the tab below from "Local Agency" to the Agency Name
3 |  |  | NOTE: In the Excel file name, replace 'Template' with the Agency Name.
4
5
6
7
8
Enter Local Agency Name Here | [48 empty] | ver: 7/12/2013
C:\Users\kwenzi\AppData\Local\Temp\[Template_FHWA_Funded_Projects_Status.xlsx]Local Agency